DOCUMENT 04 · EXECUTION

ReBridge — Phase-wise Implementation Plan

Phase 0 (tonight) → eight sprint phases with definition-of-done → 6-month roadmap.

# Phase 0 — Pre-Hackathon (do TONIGHT, before the clock starts)

- Accounts: AWS Free Tier created; Bedrock model access requested/verified in your region (this can take time — do it FIRST); Kiro installed, credits redeemed, login method locked.

- Collect 10 real test objects with varied damage: scuffed shoe, working earphones with worn pads, book with bent cover, toy missing a part, mint phone case, etc. These are your demo stars — photograph them tonight in good light.

- Customer mini-research: 8–10 hostel interviews (Doc 01 §9). Write down 3 verbatim quotes.

- Build the price-band CSV: 8–10 categories × 5 grades × age multipliers (e.g., shoes: Like New 0.55×MRP … Acceptable 0.18×). 30 minutes, unblocks the routing agent.

- Build the seeded buyer personas (~20): each with mock wishlist, recent purchases, geo, and deal-propensity — same kind of mock as the price-band CSV. Unblocks the Demand Matching Engine. ~30 minutes.

- Write the Kiro spec (entities, endpoints, screens — lift from Doc 03 §4) so scaffolding starts at minute 1.

- Repo: monorepo (api/ web/ infra/ prompts/ data/), main + feature branches, .env template, README with run commands.

- Team roles locked: P1 (you) = AI grading + routing + matching engines; P2 = backend/API/infra; P3 = frontend/UX (2-person team: P2 absorbs simple screens, cut Buyer-flow polish first).

Definition of done for Phase 0: a deployed hello-world API + blank Next.js app reachable on a URL, Bedrock returning a test response, photos of all 10 objects on disk.

# The 48-Hour Sprint — Phases 1–8

## Phase 1 · Hours 0–3 — Lock & Scaffold

| Goal | Scope frozen to the slice; skeleton deployed |
| --- | --- |
| Tasks | Feed Kiro the spec → scaffold FastAPI routes + Next.js pages; DynamoDB table + S3 bucket via IaC; presigned-upload endpoint working; write the press-release paragraph into the PRD |
| Owners | P1 prompts Kiro for API; P2 infra; P3 page shells |
| Done when | Photo uploads from browser → lands in S3 → item row in DynamoDB |
| Fallback | IaC fights you → click-ops the bucket/table, move on (note it as debt) |

## Phase 2 · Hours 3–10 — The Grading Engine (the heart)

| Goal | Photo in → strict-JSON grade out, reliably |
| --- | --- |
| Tasks | Bedrock vision call with GRADE_JSON schema; prompt includes catalog context + Amazon’s 4-tier grade definitions; blur precheck (OpenCV variance-of-Laplacian); confidence gate; iterate the prompt against ALL 10 test objects until grades feel right; log every raw response for tuning |
| Owners | P1 full-time; P2 wires the /grade endpoint + status polling |
| Done when | All 10 objects grade sensibly in <4s with valid JSON, 0 parse failures in 20 runs |
| Fallback | Bedrock access stuck → swap to Gemini/Claude API behind the SAME interface (you built this seam on purpose); cascade postponed, single model fine for demo |

## Phase 3 · Hours 10–20 — Routing + Matching Agents + Health Card

| Goal | Both agents firing on the LISTED event; signed card with QR |
| --- | --- |
| Tasks | Routing agent: LangGraph with 3 tools (price-band CSV, cost model, demand probe) → decision + price + margin math in the output. Demand Matching agent (SAME pattern — reuses the routing scaffold): score seeded buyers on intent + lifecycle + geo + price-sensitivity → ranked top-N + proactive push payload. Health Card component + HMAC sign + /verify page; review-queue table + minimal console |
| Owners | P1 both agents (matching reuses routing’s code — builds fast); P2 card/verify + LISTED event wiring; P3 starts Returns Desk UI in parallel |
| Done when | Scuffed shoe → “P2P · ₹340 · margin ₹230” AND “3 buyers within 5 km, top match 94%” + scannable QR that verifies |
| Fallback | Matching late → ship ranked list WITHOUT the proactive push (ranking is substance, push is polish). Agent slow → collapse to pure-function policy, same output format |

## Phase 4 · Hours 20–28 — The Three Flows

| Goal | Returns Desk, Rahul’s 60-second flow, Buyer view — clean and mobile-first |
| --- | --- |
| Tasks | Returns Desk: scan/select order → camera → result card → one-tap list; batch mode (grade 12 queued items); Reseller: 3 photos → single decision screen → done; Buyer: marketplace grid + listing page with Health Card front-and-center + PROACTIVE match push (“available 4 km away”) + PDP Second-Chance shelf; loading/skeleton states everywhere |
| Owners | P3 leads; P2 APIs; P1 polishes prompts + match scoring with real flow data |
| Done when | Rahul flow completes in <60s on a phone, timed; one primary action per screen; a match push renders |
| Fallback | Time crunch → cut PDP shelf, keep the match push; NEVER cut the 60s timer — it’s a pitch line |

## Phase 5 · Hours 28–34 — Hardening + Wow Details

| Goal | Demo path is bulletproof; deliberate ‘maturity’ touches |
| --- | --- |
| Tasks | Blurry-photo → retake prompt (judges love it); seed marketplace with 15 graded items; P2P “3 buyers within 5 km” screen; error states (Bedrock timeout → graceful retry); run the FULL live demo 5× with the real objects; fix the one thing that breaks twice |
| Owners | All; P1 owns the live-photo path |
| Done when | 5 consecutive clean runs of the demo script, phone + laptop |

## Phase 6 · Hours 34–40 — Deliverables

| Goal | PRD, architecture diagram, metrics — submission-grade |
| --- | --- |
| Tasks | Export Doc 03 diagram into one clean slide; finalize PRD (press release → customers → slice → metrics → roadmap); record rough demo cut to find dead air; metrics slide with Doc 02 numbers |
| Owners | P1 docs; P2/P3 UX polish from rough-cut findings |

## Phase 7 · Hours 40–46 — Demo Video + Dry Runs

| Goal | Final 3-minute video; pitch rehearsed |
| --- | --- |
| Tasks | Shoot per Doc 05 script (live object on camera!); voiceover follows working-backwards order; 2 full pitch dry-runs with Q&A from Doc 05 §4; trim to ≤3:00 |
| Done when | Video exported, watched once at 1× by the whole team without cringing |

## Phase 8 · Hours 46–48 — Buffer & Submit

- Submit EARLY. Re-read Unstop guidelines line by line. Verify every link in the submission opens in incognito. Sleep.

# Kiro Usage Strategy (per phase)

- Phases 1, 4: spec-driven generation — feed entity/endpoint/screen specs, accept scaffolds wholesale, review diffs.

- Phases 2, 3: pair-programmer mode — YOU write the prompt schemas and policy math (this is your defensible core); Kiro writes boilerplate (S3 clients, parsing, retries).

- Always: read what it generates. The finale question “why SQS here?” must be answered by you, not by your IDE. Budget: keep ~30% credits for the final 12 hours.

# Contingency Matrix

| If this happens | Do this |
| --- | --- |
| Bedrock model access not granted in time | Same-interface swap to Gemini / Claude API key (the seam exists by design); mention multi-provider as resilience |
| Grading JSON flaky | Tighten schema + add one few-shot example per failing category; temperature 0; reject-and-retry on invalid |
| Agent latency hurts demo | Pre-warm Lambda; or rule-based policy fallback with identical output format |
| Matching engine running late | Ship ranked buyer list without the proactive push (ranking = substance, push = polish); PDP shelf is the first thing to cut |
| Frontend behind at hour 30 | Cut Buyer flow polish to a single listing page + one match push; Returns Desk + Rahul flow are non-negotiable |
| Team member down | Pre-agreed: P1 absorbs agent+card; P2 absorbs all API+infra; demo script shrinks to Flows A+B |

# Post-Hackathon Roadmap (the “6 more months” answer)

| Phase | Build | Customer outcome |
| --- | --- | --- |
| M1–M2 | Fraud shield (perceptual-hash vs catalog + outbound photos, EXIF checks); few-shot category packs from review overrides | Sellers protected from swap fraud; auto-grade % climbs |
| M3–M4 | Prevention model v1 wired to PDP (“customers with your foot profile prefer size 8”) | Best return = no return; pure-margin savings |
| M5–M6 | Donation rails + ESG reporting; Grade & Resell integration pilot; Grading + Matching as a Service on AWS | Returns problem becomes an AWS revenue line |

The sprint mantra: at hour 30, if the slice isn’t end-to-end — cut scope, never add. A complete small thing beats an incomplete big thing. The judges told you this themselves.